## Sheet1
Process | Stage | Entry Criteria | Input | Activities | Responsible Role | Technique | Output | Exit Criteria | Remark
Program Benefits Management
| Program Benefits Identification |  | Business Case | * Defining: 1) objectives; 2) critical success factors * Identifying and quantifying business benefits * Developing metrics and KPI to measure actrual delivery with plan * Establishing processes for measuring progress against the benefits plan * creating tracking and communications processes to record progress and report to stakeholders |  |  | Benefits Register
| Program Benefits Analysis and Planning |  | Benefits register | 1. establish the benefits realization plan 2. Defining and prioritizing program components 3. defining KPI and associated quantitative measures 4. establish performance baseline 5. communicating performance metrics to the key stakeholders | Program Manager/Program management office/ Project manager |  | 1. program benefits realization plan 2. program architecture 3. benefits register update